## Vemana Colony PTR
Schedule (WBS No.T-2421-07-05-01-01-002)
E-Procurement Schedule for providing of 1No. additional 8 MVA PTR to the existing 1X12.5+1X8 MVA PTRs thus making total capacity of 1X12.5+2X8 MVA at 33/11KV Vemana Sub-station in Vemana Colony Section of Miyapur Sub-Division of Kukatpally Division of Medchal Circle Under T&D PTR augmentation works Summer Action plan 2025.
Sl.No. | SSR CODES | Estimate Quantity (Only figures) | Item Detailed Specification Description | Work Type eg., Earth Work, Electrical works..etc., (Upto 200 Characters) | Item Short Description | APSS/Morth CI.Number (Upto 200 characters) | Rate INR upto 2 Decimals | UOM (upto 50 Characters) | Amount INR (Upto 2 Decimals)
33 KV Bay extension
1 | SWR10205 | 8 | LOADING of LINE MATERIALS RSJoists150 x 150 mm/RailPole | LOADING work | LOADING of work | As per relevent standard specification | 176 | EA | 1408
2 | SWR10132 | 3.2 | Transport of iron materials such as R.S. Joists, Rail Poles, fabricated supports, steel, iron, flat, M.S.Channels etc., by lorries. (excluding of loading & unloading )Above 10 KM and upto 20 KM | Transport work | Transport of work | As per relevent standard specification | 412.08 | TO | 1318.656
3 | SWR10523 | 8 | UNLOADING of LINE MATERIALS RSJoists150 x150 mm/RailPol | UNLOADING work | UNLOADING of work | As per relevent standard specification | 107 | EA | 856
4 | SWR11039 | 8 | Excavation of pits in hard rock not requiring blasting. (In hard murram / rock boulders)0.76 M x 0.76M x 1.83M (2.6" x 2.6" x 6.0") | ExcavatIon work | ExcavatIon of work | As per relevent standard specification | 928 | EA | 7424
5 | SWR10868 | 3.2 | Fabrication of struc.with power drilling | Fabrication work | Fabrication of work | As per relevent standard specification | 6852 | TO | 21926.4
6 | SMR40009 | 3.2 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Supply of material cost for First coat of 1st Grade Aluminium Paint,brushes etc. | Erection work | Erection of work | As per relevent standard specification | 2181 | TO | 6979.2
7 | SWR10877 | 3.2 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Labour charges for painting including scratching and cleaning of Substation structures of 1st coat of Aluminium | Erection work | Erection of work | As per relevent standard specification | 851 | TO | 2723.2
8 | SMR40010 | 3.2 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Supply of material cost for Second coat of 1st Grade Aluminium Paint,brushes, etc. | Erection work | Erection of work | As per relevent standard specification | 1293 | TO | 4137.6
9 | SWR10879 | 3.2 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Supply of material cost for Second coat of 1st Grade Aluminium Paint,brushes, etc. | Erection work | Erection of work | As per relevent standard specification | 482 | TO | 1542.4
10 | SWR10867 | 3.2 | Alligning the Main/Aux. structures. | Erection work | Erection of work | As per relevent standard specification | 1470 | TO | 4704
11 | SWR10348 | 8 | Erection of RS Joist 150 x 150 mm | Erection work | Erection of work | As per relevent standard specification | 1952.61 | EA | 15620.88
12 | SWR10356 | 8.879 | Mass concreting of supports erected with CC (1:4:8) using 40 mm, HB G metal including the cost of metal, sand,Cement and curing etc.Including the cost of cement | Erection work | Erection of work | As per relevent standard specification | 6579 | M3 | 58414.941
13 | SWR10862 | 4.62 | Plastering 2 Coats,20/16mm(1:6)(1:4) | Erection work | Erection of work | As per relevent standard specification | 373 | M2 | 1723.26
14 | SWR11089 | 8 | Paint of coping with 2 coats of white cement incl cost of paints etc. | Erection work | Erection of work | As per relevent standard specification | 48 | EA | 384
15 | SWR10204 | 4 | LOADING of R.S. Joists 175 x 85 mm | LOADING work | LOADING of work | As per relevent standard specification | 76 | EA | 304
16 | SWR10132 | 1 | TRANSPORT OF STEEL 10 TO 20KM | Transport work | Transport of work | As per relevent standard specification | 412.08 | TO | 412.08
17 | SWR10522 | 4 | UNLOADING of R.S. Joists 175 x 85 mm | UNLOADING work | UNLOADING of work | As per relevent standard specification | 50 | EA | 200
18 | SWR11037 | 4 | Excavation of pits in hard rock not requiring blasting. (In hard murram / rock boulders)0.76 M x 0.76M x 1.52M (2.6" x 2.6" x 5.0') 0.88 cum | Excavation work | Excavation of work | As per relevent standard specification | 793 | EA | 3172
19 | SWR10868 | 1 | Fabrication of struc.with power drilling | Fabrication work | Fabrication of work | As per relevent standard specification | 6852 | TO | 6852
20 | SMR40009 | 1 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Supply of material cost for First coat of 1st Grade Aluminium Paint,brushes etc. | Erection work | Erection of work | As per relevent standard specification | 2181 | TO | 2181
21 | SWR10877 | 1 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Labour charges for painting including scratching and cleaning of Substation structures of 1st coat of Aluminium | Erection work | Erection of work | As per relevent standard specification | 851 | TO | 851
22 | SMR40010 | 1 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied (*)Supply of material cost for Second coat of 1st Grade Aluminium Paint,brushes, etc. | Erection work | Erection of work | As per relevent standard specification | 1293 | TO | 1293
23 | SWR10879 | 1 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Labour charges for painting including scratching and cleaning of Substation structures of 2nd coat of Aluminium . | Erection work | Erection of work | As per relevent standard specification | 482 | TO | 482
24 | SWR10867 | 1 | Alligning the Main/Aux. structures. | Erection work | Erection of work | As per relevent standard specification | 1470 | TO | 1470
25 | SWR11267 | 4 | Erection of pole in position, aligning and setting to work, fixing of cross arms and top clamps, earthing of supports,back filling with earth and stones properly ramming including transport of materials from road side to location excluding pit excavation Box pole 12 Mtr | Erection work | Erection of work | As per relevent standard specification | 3901.37 | EA | 15605.48
26 | SWR10356 | 1.66 | Mass concreting of supports erected with CC (1:4:8) using 40 mm, HB G metal including the cost of metal, sand,Cement and curing etc.Including the cost of cement | Erection work | Erection of work | As per relevent standard specification | 6579 | M3 | 10921.14
27 | SWR10862 | 2.31 | Plastering 2 coats, 20/16 mm (1:6)/(1:4) | Erection work | Erection of work | As per relevent standard specification | 373 | M2 | 861.63
28 | SWR11089 | 4 | Paint of coping with 2 coats of white cement incl cost of paints etc. | Erection work | Erection of work | As per relevent standard specification | 48 | EA | 192
29 | SWR10206 | 2.6 | LOADING of MS Channel,Angles,Flats&Rods | LOADING work | LOADING of work | As per relevent standard specification | 221 | TO | 574.6
30 | SWR10132 | 2.6 | Transport of iron materials such as R.S. Joists, Rail Poles, fabricated supports, steel, iron, flat, M.S.Channels etc., by lorries. (excluding of loading & unloading )Above 10 KM and upto 20 KM | Transport work | Transport of work | As per relevent standard specification | 412.08 | TO | 1071.408
31 | SWR10524 | 2.6 | UNLOADING of MS Channel,Angles,Flats&Rod | UNLOADING work | UNLOADING of work | As per relevent standard specification | 185 | TO | 481
32 | SWR10868 | 2.6 | Fabrication of Main and Auxiliary structures with power drilling using raw steel such as M.S.Angles, Plates, Channels, R.S.Joists, including the supply and fabrication of 6mm base and top plate for Box pole to the RSJoist poles excluding cost of Mild Steel and transport charges to substation site, including erection. | Fabrication work | Fabrication of work | As per relevent standard specification | 6852 | TO | 17815.2
33 | SMR40009 | 2.6 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Supply of material cost for First coat of 1st Grade Aluminium Paint,brushes etc. | Erection work | Erection of work | As per relevent standard specification | 2181 | TO | 5670.6
34 | SWR10877 | 2.6 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Labour charges for painting including scratching and cleaning of Substation structures of 1st coat of Aluminium | Erection work | Erection of work | As per relevent standard specification | 851 | TO | 2212.6
35 | SMR40010 | 2.6 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied (*)Supply of material cost for Second coat of 1st Grade Aluminium Paint,brushes, etc. | Erection work | Erection of work | As per relevent standard specification | 1293 | TO | 3361.8
36 | SWR10879 | 2.6 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Labour charges for painting including scratching and cleaning of Substation structures of 2nd coat of Aluminium . | Erection work | Erection of work | As per relevent standard specification | 482 | TO | 1253.2
37 | SWR10867 | 2.6 | Alligning the Main/Aux. structures. | Erection work | Erection of work | As per relevent standard specification | 1470 | TO | 3822
38 | SWR10239 | 3 | LOADING of 33 KV AB SWCH Con 400/800 A | LOADING work | LOADING of work | As per relevent standard specification | 126 | EA | 378
39 | SWR11861 | 1 | Transport of conductor drums, cable drums, fragile material such as kiosks, VCBs, control panels,current transformers, boosters, lightning arrestors, insulators, transformers, meters (which are less in weight and occupy more space) (excluding of loading unloading)Note: 1). It will be treated as full load of 10 MT and paid for 10 MT.2). For 3 Ton vehicle : 50% of the following rates Above 10 Km and upto 20 Km with Lorry for each trip | Transport work | Transport of work | As per relevent standard specification | 3299.7 | EA | 3299.7
40 | SWR10557 | 3 | UNLOADING of 33 KV AB SWCH Con 400/800 A | UNLOADING work | UNLOADING of work | As per relevent standard specification | 79 | EA | 237
41 | SWR10392 | 3 | Erection of AB Switch and aligment complete Erection of 33 KV AB Switch including alignment and earthing | Erection work | Erection of work | As per relevent standard specification | 4500 | EA | 13500
42 | SWR10881 | 3 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Painting of operating rods of 33kV, 11kV AB switches with post office red colour (including cost of paint) | Erection work | Erection of work | As per relevent standard specification | 142 | EA | 426
43 | SWR12331 | 3 | Making of coil earthing pole with 8mm GI wireNut&Bolts for AB Switch | Earthing work | Earthing of work | As per relevent standard specification | 146.63 | EA | 439.89
44 | SWR10200 | 3 | LOADING of 33/11 KV CTs/ PTs | LOADING work | LOADING of work | As per relevent standard specification | 165 | EA | 495
45 | SWR11861 | 3 | Transport of conductor drums, cable drums, fragile material such as kiosks, VCBs, control panels,current transformers, boosters, lightning arrestors, insulators, transformers, meters (which are less in weight and occupy more space) (excluding of loading unloading)Note: 1). It will be treated as full load of 10 MT and paid for 10 MT.2). For 3 Ton vehicle : 50% of the following rates Above 10 Km and upto 20 Km with Lorry for each trip | Transport work | Transport of work | As per relevent standard specification | 3299.7 | EA | 9899.1
46 | SWR10518 | 3 | UNLOADING of 33/11 KV CTs/ PTs | UNLOADING work | UNLOADING of work | As per relevent standard specification | 128 | EA | 384
47 | SWR10401 | 1 | Erection of AB Switches, VCBs, LAs, PTs, CTs, DTRs etc Erection of 33 KV single phase PTs | Erection work | Erection of work | As per relevent standard specification | 1079 | SET | 1079
48 | SWR10266 | 3 | LOADING of 33 KV10 KA LAs Station type | LOADING work | LOADING of work | As per relevent standard specification | 41 | EA | 123
49 | SWR11861 | 3 | Transport of conductor drums, cable drums, fragile material such as kiosks, VCBs, control panels,current transformers, boosters, lightning arrestors, insulators, transformers, meters (which are less in weight and occupy more space) (excluding of loading unloading)Note: 1). It will be treated as full load of 10 MT and paid for 10 MT.2). For 3 Ton vehicle : 50% of the following rates Above 10 Km and upto 20 Km with Lorry for each trip | Transport work | Transport of work | As per relevent standard specification | 3299.7 | EA | 9899.1
50 | SWR10584 | 3 | UNLOADING of 33 KV10 KA LAs Station type | UNLOADING work | UNLOADING of work | As per relevent standard specification | 35 | EA | 105
51 | SWR10396 | 1 | Erection of AB Switches, VCBs, LAs, PTs, CTs, DTRs etc Erection of 33 KV LAS station/Line type including earthing | Erection work | Erection of work | As per relevent standard specification | 880 | SET | 880
52 | SWR10198 | 1 | LOADING of 33 KV VCBs&Panel boards | LOADING work | LOADING of work | As per relevent standard specification | 1024 | EA | 1024
53 | SWR11861 | 1 | Transport of conductor drums, cable drums, fragile material such as kiosks, VCBs, control panels,current transformers, boosters, lightning arrestors, insulators, transformers, meters (which are less in weight and occupy more space) (excluding of loading unloading)Note: 1). It will be treated as full load of 10 MT and paid for 10 MT.2). For 3 Ton vehicle : 50% of the following rates Above 10 Km and upto 20 Km with Lorry for each trip | Transport work | Transport of work | As per relevent standard specification | 3299.7 | EA | 3299.7
54 | SWR10516 | 1 | UNLOADING of 33 KV VCBs&Panel boards | UNLOADING work | UNLOADING of work | As per relevent standard specification | 1044.48 | EA | 1044.48
55 | SWR20768 | 6.292 | Earth work excavation of in all soils except hard rock requiring blasting. | Earthing work | Earthing of work | As per relevent standard specification | 345 | M3 | 2170.74
56 | SWR20685 | 6.292 | Cement concrete with 40MM metal VCB plin | Erection work | Erection of work | As per relevent standard specification | 5160 | M3 | 32466.72
57 | SWR10460 | 1 | Erection of AB Switches, VCBs, LAs, PTs, CTs, DTRs etc Erection of 33 KV VCB with Control Panel | Erection work | Erection of work | As per relevent standard specification | 12500 | EA | 12500
58 | SWR10613 | 1 | LOADING of 8 MVA PTR | LOADING work | LOADING of work | As per relevent standard specification | 5805.84 | EA | 5805.84
59 | SWR10854 | 1 | Transport of Power transformers (0 to 100 KM) from one place to another place in GHMC Area.(excluding of loading & unloading )8MVA power transformer | Transport work | Transport of work | As per relevent standard specification | 21945 | EA | 21945
60 | SWR10627 | 1 | UNLOADING of 8 MVA PTR | UNLOADING work | UNLOADING of work | As per relevent standard specification | 5805.84 | EA | 5805.84
61 | SMR22718 | 400 | S/o rail poles 90/105lb (250x2N) | Erection work | Erection of work | As per relevent standard specification | 47.27 | KG | 18908
62 | SWR10344 | 8 | Erection of pole in position, aligning and setting to work, fixing of cross arms and top clamps, earthing of supports,back filling with earth and stones properly ramming including transport of materials from road side to location excluding pit excavation Rail pole 90 lbs | Erection work | Erection of work | As per relevent standard specification | 3510 | EA | 28080
63 | SWR21321 | 1 | Erection of PTR on constructed plinth Erection of 8 MVA PTR | Erection work | Erection of work | As per relevent standard specification | 49480.2 | EA | 49480.2
64 | SMR24910 | 0.13 | Extention of 33KV Bay at 132/33KV Sub-station Zebra condutor | Extention work | Extention of work | As per relevent standard specification | 299369 | KM | 38917.97
65 | SMR11915 | 18 | Supply of Tension Hardware 3 Bolted for single Zebra/panther with 150 mm spacing | Supply work | Supply of work | As per relevent standard specification | 2055 | SET | 36990
66 | SMR22473 | 18 | Supply of clamps as per IS 5561- 1970 , 12mm thickness with Alluminum and Alluminum alloy Supply of I Bolts | Supply work | Supply of work | As per relevent standard specification | 294 | EA | 5292
67 | SMR40011 | 27 | Supply of clamps as per IS 5561- 1970 , 12mm thickness with Alluminum and Alluminum alloy A6 of IS 617 1994 & hot dip galvanised with Nuts & Bolts including spring with hot dip galvanised bolts and double nuts with spring and flat washers of size M10 x 65 i.e(3/8" x 21/2 " to suit for panther ACSR on all three ways /on one side and Zebra ACSR on take off side or any other combination for carrying 800 A current rating . | Supply work | Supply of work | As per relevent standard specification | 299 | EA | 8073
68 | SWR21240 | 6 | Hoisting of Insulators and hardware, stretching the conductor and stringing of 33 kV bus comprising of three phases with Single Zebra/panther conductor to a tension of 450kgs.(Bus section of 4.5mt) | Erection work | Erection of work | As per relevent standard specification | 781 | EA | 4686
69 | SWR10404 | 54 | Stringing of bus with panther conductor including jumpering etc., complete to all the equipment in SS fixing to all clamps and equipment.(3 Conductors) | Erection work | Erection of work | As per relevent standard specification | 327.68 | M | 17694.72
70 | SWR10884 | 30 | Connection of equipment to bus and or another equipment with single zebra/Panther conductor including measuring, cutting,clamping and hoisting of suspension insulator assembly to support the conductor wherever necessary. | Erection work | Erection of work | As per relevent standard specification | 224 | EA | 6720
71 | SWR10917 | 75 | Labour for Fixing of all types of clamps | Civil work | Civil of work | As per relevent standard specification | 65 | EA | 4875
72 | SWR34179 | 24 | Hire-JCB to Level & Clear the Site | Civil work | Civil of work | As per relevent standard specification | 2165 | H | 51960
73 | SWR33015 | 65.25 | Excavation in Ordinary Soil | Civil work | Civil of work | As per relevent standard specification | 486 | M3 | 31711.5
74 | SWR33028 | 13.62 | PCC with 40mm Metal (1:4:8) | Civil work | Civil of work | As per relevent standard specification | 4706 | M3 | 64095.72
75 | SWR33041 | 94 | CRS Masonary CM(1:6) 2nd Sort | Civil work | Civil of work | As per relevent standard specification | 4925 | M3 | 462950
76 | SWR33030 | 2.61 | PCC with 20mm Metal (1:2:4) | Civil work | Civil of work | As per relevent standard specification | 6449 | M3 | 16831.89
77 | SWR33052 | 558.9 | S&Filling with Borrowed Gravel | Civil work | Civil of work | As per relevent standard specification | 480 | M3 | 268272
78 | SWR33184 | 87 | Raised Pointing to CRS Masonary CM(1:3) | Civil work | Civil of work | As per relevent standard specification | 117 | M2 | 10179
79 | SWR33057 | 59.61 | S&Spreading of 20mm HBG Metal | Civil work | Civil of work | As per relevent standard specification | 1543 | M3 | 91978.23
80 | SWR33403 | 121.8 | S&F MS Security Fencing Mesh (2"X2") | Civil work | Civil of work | As per relevent standard specification | 2310 | M2 | 281358
81 | SWR33068 | 6.17 | Brick Masonary in CM(1:6) GFloor | Civil work | Civil of work | As per relevent standard specification | 7209 | M3 | 44479.53
82 | SWR33163 | 126.28 | Plastering 20mm (16mm+4mm)GFloor | Civil work | Civil of work | As per relevent standard specification | 520 | M2 | 65665.6
83 | SWR33264 | 2 | S&F MT Wood Frame & Door-Laminate | Civil work | Civil of work | As per relevent standard specification | 7314 | M2 | 14628
84 | SWR33333 | 61.78 | Painting with OBD 2Coats+Primer | Civil work | Civil of work | As per relevent standard specification | 146 | M2 | 9019.88
85 | SWR33363 | 9.9 | Paint-PlasticEmulsn2Coat+Primer-ExtrnlGF | Civil work | Civil of work | As per relevent standard specification | 245 | M2 | 2425.5
86 | SWR33329 | 87 | Painting with SuryaCem of 3 Coat | Civil work | Civil of work | As per relevent standard specification | 85 | M2 | 7395
87 | SWR34361 | 6 | S&F 15.90mm OD CPVC Pipe-SDR 11 | Civil work | Civil of work | As per relevent standard specification | 239 | M | 1434
88 | SWR34362 | 75 | S&F 22.20mm OD CPVC Pipe-SDR 11 | Civil work | Civil of work | As per relevent standard specification | 313 | M | 23475
89 | SWR34363 | 45 | S&F 28.60mm OD CPVC Pipe-SDR 11 | Civil work | Civil of work | As per relevent standard specification | 410 | M | 18450
90 | SWR34346 | 2 | S&F-25mm GM/Bronze Ball Valve | Civil work | Civil of work | As per relevent standard specification | 466 | EA | 932
91 | SWR34329 | 10 | S&F-15mm Bib Tap 400gm Full turn | Civil work | Civil of work | As per relevent standard specification | 298 | EA | 2980
92 | SWR34470 | 19.12 | Seigniorage Charges - Sand | Civil work | Civil of work | As per relevent standard specification | 40 | M3 | 764.8
93 | SWR34928 | 19.12 | Seigniorage Charges for M-Sand | Civil work | Civil of work | As per relevent standard specification | 97.5 | M3 | 1864.2
94 | SWR34471 | 177.62 | Seigniorage Charges - Metal | Civil work | Civil of work | As per relevent standard specification | 97.5 | M3 | 17317.95
95 | SWR34472 | 558.9 | Seigniorage Charges - Gravel | Civil work | Civil of work | As per relevent standard specification | 30 | M3 | 16767
Schedule Cost. (Excluding GST) | [8 empty] | 2064081.075
11KV Bay extension
1 | SWR10205 | 17 | Loading of R.S. Joists 150 x 150mm / Rail poles | LOADING work | LOADING of work | As per relevent standard specification | 176 | EA | 2992
2 | SWR10132 | 7.3 | Transport of iron materials such as R.S. Joists, Rail Poles, fabricated supports, steel, iron, flat, M.S. Channels etc., by lorries. (excluding of loading & unloading ) Above 10 KM and upto 20 KM | Transport work | Transport of work | As per relevent standard specification | 412.08 | TO | 3008.184
3 | SWR10523 | 17 | Un loading of R.S. Joists 150 x 150mm / Rail poles | UNLOADING work | UNLOADING of work | As per relevent standard specification | 107 | EA | 1819
4 | SWR11039 | 17 | Excavation of pits in hard rock not requiring blasting. (In hard murram / rock boulders) 0.76 M x 0.76M x 1.83M (2.6" x 2.6" x 6.0") | Excavation work | Excavation of work | As per relevent standard specification | 928 | EA | 15776
5 | SWR10868 | 7.3 | Fabrication & erection of Channels, Fabrication of Main and Auxiliary structures with power drilling using raw steel such as M.S.Angles, Plates, Channels, R.S.Joists, including the supply and fabrication of 6mm base and top plate for Box pole to the RS-Joist poles excluding cost of Mild Steel and transport charges to substation site, including erection. | Fabrication work | Fabrication of work | As per relevent standard specification | 6852 | TO | 50019.6
6 | SMR40009 | 7.3 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied before erection of sub-station structures and 2nd coat after stringing and half round welding including cost of paint, cost of brushes, labour charges etc., complete.Supply of material cost for First coat of 1st Grade Aluminium Paint, brushes etc. | Erection work | Erection of work | As per relevent standard specification | 2181 | TO | 15921.3
7 | SWR10877 | 7.3 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied before erection of sub-station structures and 2nd coat after stringing and half round welding including cost of paint, cost of brushes, labour charges etc., complete. Labour charges for painting including scratching and cleaning of Sub-station structures of 1st coat of Aluminium | Erection work | Erection of work | As per relevent standard specification | 851 | TO | 6212.3
8 | SMR40010 | 7.3 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied before erection of sub-station structures and 2nd coat after stringing and half round welding including cost of paint, cost of brushes, labour charges etc., complete. (*)Supply of material cost for Second coat of 1st Grade Aluminium Paint, brushes, etc. | Erection work | Erection of work | As per relevent standard specification | 1293 | TO | 9438.9
9 | SWR10879 | 7.3 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied before erection of sub-station structures and 2nd coat after stringing and half round welding including cost of paint, cost of brushes, labour charges etc., complete. (*) Labour charges for painting including scratching and cleaning of Sub-station structures of 2nd coat of Aluminium . | Erection work | Erection of work | As per relevent standard specification | 482 | TO | 3518.6
10 | SWR10867 | 7.3 | Alligning the Main/Aux. structures. | Erection work | Erection of work | As per relevent standard specification | 1470 | TO | 10731
11 | SWR10348 | 17 | Erection of pole in position, aligning and setting to work, fixing of cross arms and top clamps, earthing of supports, back filling with earth and stones properly ramming including transport of materials from road side to location excluding pit excavation R.S. Joists 150 x 150 mm | Erection work | Erection of work | As per relevent standard specification | 1952.61 | EA | 33194.37
12 | SWR10356 | 18.87 | Mass concreting of supports erected with CC (1:4:8) using 40 mm, HB G metal including the cost of metal, sand,Cement and curing etc.Including the cost of cement | Erection work | Erection of work | As per relevent standard specification | 6579 | M3 | 124145.73
13 | SWR10862 | 9.82 | Plastering 2 Coats,20/16mm(1:6)(1:4) | Erection work | Erection of work | As per relevent standard specification | 373 | M2 | 3662.86
14 | SWR11089 | 17 | Painting of poles Paint of coping with 2 coats of white cement incl cost of paints etc. | Erection work | Erection of work | As per relevent standard specification | 48 | EA | 816
15 | SWR10206 | 3.75 | Loading of M.S.Channels, Angles, Flats & Rods etc., | LOADING work | LOADING of work | As per relevent standard specification | 221 | TO | 828.75
16 | SWR10132 | 3.75 | Transport of iron materials such as R.S. Joists, Rail Poles, fabricated supports, steel, iron, flat, M.S. Channels etc., by lorries. (excluding of loading & unloading ) Above 10 KM and upto 20 KM | Transport work | Transport of work | As per relevent standard specification | 412.08 | TO | 1545.3
17 | SWR10524 | 3.75 | Un loading of M.S.Channels, Angles, Flats & Rods etc., | UNLOADING work | UNLOADING of work | As per relevent standard specification | 185 | TO | 693.75
18 | SWR10868 | 3.75 | Fabrication & erection of Channels,Fabrication of Main and Auxiliary structures with power drilling using raw steel such as M.S.Angles, Plates, Channels, R.S.Joists, including the supply and fabrication of 6mm base and top plate for Box pole to the RS-Joist poles excluding cost of Mild Steel and transport charges to substation site, including erection. | Fabrication work | Fabrication of work | As per relevent standard specification | 6852 | TO | 25695
19 | SMR40009 | 3.75 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied before erection of sub-station structures and 2nd coat after stringing and half round welding including cost of paint, cost of brushes, labour charges etc., complete.Supply of material cost for First coat of 1st Grade Aluminium Paint, brushes etc. | Erection work | Erection of work | As per relevent standard specification | 2181 | TO | 8178.75
20 | SWR10877 | 3.75 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied before erection of sub-station structures and 2nd coat after stringing and half round welding including cost of paint, cost of brushes, labour charges etc., complete. Labour charges for painting including scratching and cleaning of Sub-station structures of 1st coat of Aluminium Labour charges for painting including scratching and cleaning of Sub-station structures of 1st coat of Aluminium | Erection work | Erection of work | As per relevent standard specification | 851 | TO | 3191.25
21 | SMR40010 | 3.75 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied before erection of sub-station structures and 2nd coat after stringing and half round welding including cost of paint, cost of brushes, labour charges etc., mplete.(*)Supply of material cost for Second coat of 1st Grade Aluminium Paint, brushes, etc. | Erection work | Erection of work | As per relevent standard specification | 1293 | TO | 4848.75
22 | SWR10879 | 3.75 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied before erection of sub-station structures and 2nd coat after stringing and half round welding including cost of paint, cost of brushes, labour charges etc., complete. (*) Labour charges for painting including scratching and cleaning of Sub-station structures of 2nd coat of Aluminium | Erection work | Erection of work | As per relevent standard specification | 482 | TO | 1807.5
23 | SWR10867 | 3.75 | Alligning the Main/Aux. structures. | Erection work | Erection of work | As per relevent standard specification | 1470 | TO | 5512.5
24 | SWR10238 | 10 | LOADING of 11 KV AB SWCH Con 200/400 A | LOADING work | LOADING of work | As per relevent standard specification | 80 | EA | 800
25 | SWR11861 | 2 | Transport of conductor drums, cable drums, fragile material such as kiosks, VCBs, control panels, current transformers, boosters, lightning arrestors, insulators, transformers, meters (which are less in weight and occupy more space) (excluding of loading unloading Above 10 Km and upto 20 Km with Lorry for each trip | Transport work | Transport of work | As per relevent standard specification | 3299.7 | EA | 6599.4
26 | SWR10556 | 10 | Un loading of 11KV AB Switch Conventional type | UNLOADING work | UNLOADING of work | As per relevent standard specification | 80 | EA | 800
27 | SWR21277 | 10 | Erection of AB Switch and aligment complete Ere 11KV 800A double throw AB Switches | Erection work | Erection of work | As per relevent standard specification | 3500 | EA | 35000
28 | SWR10393 | 2 | Erection of AB Switch and aligment complete Erection of 11KV 400/200A Conventional type AB Switch including fixing of cross angles and alignment complete | Erection work | Erection of work | As per relevent standard specification | 3200 | EA | 6400
29 | SWR10201 | 1 | Loading of 11 KV CT - PT Sets | LOADING work | LOADING of work | As per relevent standard specification | 190 | EA | 190
30 | SWR10519 | 1 | UNLOADING of 11 KV CT - PT Sets | UNLOADING work | UNLOADING of work | As per relevent standard specification | 101 | EA | 101
31 | SWR10402 | 1 | Erection of AB Switches, VCBs, LAs, PTs, CTs, DTRs etc Erection of 11 KV three phase PTs | Erection work | Erection of work | As per relevent standard specification | 800 | SET | 800
32 | SWR10264 | 3 | Loading of 11 KV, 10 KA LAs Station type | LOADING work | LOADING of work | As per relevent standard specification | 32 | EA | 96
33 | SWR10582 | 3 | Un loading of 11 KV, 10 KA LAs Station type | UNLOADING work | UNLOADING of work | As per relevent standard specification | 32 | EA | 96
34 | SWR10397 | 1 | Erection of AB Switches, VCBs, LAs, PTs, CTs, DTRs etc Erection of 11 KV LAS station type including earthing | Erection work | Erection of work | As per relevent standard specification | 559 | SET | 559
35 | SWR10398 | 4 | Erection of AB Switches, VCBs, LAs, PTs, CTs, DTRs etc Erection of 11 KV LAS line type including earthing | Erection work | Erection of work | As per relevent standard specification | 505 | SET | 2020
36 | SWR10199 | 5 | Loading of 11 KV VCBs along with Panel boards | LOADING work | LOADING of work | As per relevent standard specification | 1024 | EA | 5120
37 | SWR11861 | 3 | Transport of conductor drums, cable drums, fragile material such as kiosks, VCBs, control panels, current transformers, boosters, lightning arrestors, insulators, transformers, meters (which are less in weight and occupy more space) (excluding of loading unloading) Note: 1). It will be treated as full load of 10 MT and paid for 10 MT. 2). For 3 Ton vehicle : 50% of the following rates Above 10 Km and upto 20 Km with Lorry for each trip | Transport work | Transport of work | As per relevent standard specification | 3299.7 | EA | 9899.1
38 | SWR10517 | 5 | UNLOADING of 11 KV VCBs&Panel boards | UNLOADING work | UNLOADING of work | As per relevent standard specification | 1044.48 | EA | 5222.4
39 | SWR20685 | 30 | Cement concrete 1:3:6 ration with 40 MML HBG metal including the cost of all materials and labour complete 1.8 x 1.8 x 0.75 cum for VCB Plinth | Erection work | Erection of work | As per relevent standard specification | 5160 | M3 | 154800
40 | SWR10461 | 5 | Erection of AB Switches, VCBs, LAs, PTs, CTs, DTRs etc Erection of 11 KV VCB with Control Panel | Erection work | Erection of work | As per relevent standard specification | 12000 | EA | 60000
41 | SMR11915 | 12 | S-Tension HW 3Bolt 1Zebra/Pnthr 150mm | Supply work | Supply of work | As per relevent standard specification | 2055 | SET | 24660
42 | SMR22473 | 12 | Supply of clamps as per IS 5561- 1970 , 12mm thickness with Alluminum and Alluminum alloy conforming to A6 of IS 617 1994 & hot dip galvanised with Nuts & Bolts including spring washers conforming to IS 2633-1964, IS 1363-1967, IS1367-1961) , Supply of I Bolts | Supply work | Supply of work | As per relevent standard specification | 294 | EA | 3528
43 | SMR40011 | 45 | Supply of various Clamps Supply of clamps as per IS 5561- 1970 , 12mm thickness with Alluminum and Alluminum alloy conforming to A6 of IS 617 1994 & hot dip galvanised with Nuts & Bolts including spring washers conforming to IS 2633-1964, IS 1363-1967, IS1367-1961) ,Supply of Alluminum alloy T clamps conforming to A6 of IS 617,4 bolted with hot dip galvanised bolts and double nuts with spring and flat washers of size M10 x 65 i.e(3/8" x 21/2 " to suit for panther ACSR on all three ways /on one side and Zebra ACSR on take off side or any other combination for carrying 800 A current rating . | Supply work | Supply of work | As per relevent standard specification | 299 | EA | 13455
44 | SWR21241 | 2 | Bus Stringing Hoisting of Insulators and hardware, stretching the conductor and stringing of 11 kV bus comprising of three phases with Single Zebra/panther conductor to a tension of 450kgs.(Bus section of 3.5mt) | Stringing work | Stringing of work | As per relevent standard specification | 507 | EA | 1014
45 | SWR10404 | 40 | Stringing of bus with panther conductor including jumpering etc., complete to all the equipment in SS fixing to all clamps and equipment.(3 Conductors) | Stringing work | Stringing of work | As per relevent standard specification | 327.68 | M | 13107.2
46 | SWR10884 | 45 | Bus StringingConnection of equipment to bus and or another equipment with single zebra/Panther conductor including measuring, cutting,clamping and hoisting of suspension insulator assembly to support the conductor wherever necessary. | Stringing work | Stringing of work | As per relevent standard specification | 224 | EA | 10080
47 | SWR10917 | 57 | Labour for Fixing of all types of clamps | Stringing work | Stringing of work | As per relevent standard specification | 65 | EA | 3705
48 | SWR10206 | 1.3 | LOADING of MS Channel,Angles,Flats&Rods | LOADING work | LOADING of work | As per relevent standard specification | 221 | TO | 287.3
49 | SWR10132 | 1.3 | Transport of iron materials such as R.S. Joists, Rail Poles, fabricated supports, steel, iron, flat, M.S. Channels etc., by lorries. (excluding of loading & unloading )Above 10 KM and upto 20 KM | Transport work | Transport of work | As per relevent standard specification | 412.08 | TO | 535.704
50 | SWR10524 | 1.3 | UNLOADING of MS Channel,Angles,Flats&Rod | UNLOADING work | UNLOADING of work | As per relevent standard specification | 185 | TO | 240.5
51 | SWR10920 | 434 | Laying of earth mat including excavation of trenches of depth 600mm, welding, connecting to equipment and connecting lightning shield to earth mat and earthing of fence posts, drilling and connecting earth rods including connecting cast iron pipes with the following sizes of MS Flats /GI Flats. including fabrication. 75x 8mm MS Flat / GI Flat. | Laying work | Laying of work | As per relevent standard specification | 65 | RMT | 28210
52 | SWR10919 | 494 | M.S./ G.I. Flat 50x6mm / 50 x 8 mm ( Above ground) | Earthing work | Earthing of work | As per relevent standard specification | 41 | RMT | 20254
53 | SMR11482 | 24 | Fabrication and connecting to risers from earth mat to structures, equipment, marshalling boxes, electrical panels, PLCC panels, fencing posts etc. M.S./ G.I. Flat 50x6mm / 50 x 8 mm ( Above ground) | Earthing work | Earthing of work | As per relevent standard specification | 3486 | EA | 83664
54 | SWR10357 | 24 | Providing of Earthing Providing of earthing with excavation of earth pit (0.6 x0.6x2.4 Mts.) duly filling with bentonite, earth , running of earth wire etc., complete, including cost of bentonite and excluding cost of RCC collar of size 0.75M dia x 0.5 M height | Earthing work | Earthing of work | As per relevent standard specification | 1234.2 | EA | 29620.8
55 | SWR10359 | 24 | Providing of RCC collar to earth pit. Providing of RCC Collar guarding to the existing earth pits with damaged masonry including dismantling and removing of existing masonry and fixing the RCC collar of 0.60 M dia X 0.50 M height | Earthing work | Earthing of work | As per relevent standard specification | 386 | EA | 9264
56 | SMR40033 | 1 | Supply of Copper Flexible jumper with 75 X 8 of length 250 mm at neutral of Power tranformer end and 50 X 6 of length 50mm two Nos at double neutral end duly brasing with flexible jumper of capacity of 5kA/3 sec for power transformer neutral. | Supply work | Supply of work | As per relevent standard specification | 4725 | EA | 4725
57 | SWR11892 | 1 | Providing of earthing with various types of earth electrodes Providing of double earthing for neutral with flexible copper jumpers including arrangement by fixing M.S.Channel 100x50mm. | Earthing work | Earthing of work | As per relevent standard specification | 1323 | EA | 1323
58 | SWR11702 | 3 | Load-LT AB Cb 3x16+25sqmm | LOADING work | LOADING of work | As per relevent standard specification | 200 | DR | 600
59 | SWR11861 | 1 | Transport of conductor drums, cable drums, fragile material such as kiosks, VCBs, control panels, current transformers, boosters, lightning arrestors, insulators, transformers, meters (which are less in weight and occupy more space) (excluding of loading unloading) Note: 1). It will be treated as full load of 10 MT and paid for 10 MT. 2). For 3 Ton vehicle : 50% of the following rates Above 10 Km and upto 20 Km with Lorry for each trip | Transport work | Transport of work | As per relevent standard specification | 3299.7 | EA | 3299.7
60 | SWR11713 | 3 | UnLoad-LT AB Cb 3x16+25sqmm | UNLOADING work | UNLOADING of work | As per relevent standard specification | 204 | DR | 612
61 | SWR22093 | 80 | Providing of control cable trench as per DATA-XII | Earthing work | Earthing of work | As per relevent standard specification | 3148 | RMT | 251840
62 | SWR11879 | 1466 | Control CableLaying of 4 core/10 core 2.5 sq. mm.Copper control cable in aready excavation trench including cost of providing single compress glands at both ends . | Laying work | Laying of work | As per relevent standard specification | 27 | M | 39582
63 | SWR12510 | 270 | L-Cable Termination to Switchgear | Laying work | Laying of work | As per relevent standard specification | 27 | EA | 7290
64 | SMR40048 | 2 | Marshalling Box Supply of FRP PT Marshalling Box | Laying work | Laying of work | As per relevent standard specification | 4463 | EA | 8926
65 | SWR10940 | 2 | Marshalling Box Erection of Marshalling boxes | Laying work | Laying of work | As per relevent standard specification | 374.85 | EA | 749.7
66 | SWR11861 | 1 | Transport of conductor drums, cable drums, fragile material such as kiosks, VCBs, control panels, current transformers, boosters, lightning arrestors, insulators, transformers, meters (which are less in weight and occupy more space) (excluding of loading unloading) Note: 1). It will be treated as full load of 10 MT and paid for 10 MT. 2). For 3 Ton vehicle : 50% of the following rates Above 10 Km and upto 20 Km with Lorry for each trip | Transport work | Transport of work | As per relevent standard specification | 3299.7 | EA | 3299.7
67 | SMR40044 | 1 | Control PanelsSupply of DC Annunciation & relay panel for 10 feeder panel including the cost of LED Indiacation lamps, VAA auxilairy relays, Electronic Hooters complete as per specification. | Supply work | Supply of work | As per relevent standard specification | 42500 | EA | 42500
68 | SMR40045 | 1 | Control Panels Supply of AC Supply panel inluding providing of changeover switch, SFU, metering unit, 32 A three phase MCB, 16 A Single phase MCB complete as per specification. | Supply work | Supply of work | As per relevent standard specification | 42000 | EA | 42000
69 | SWR20025 | 2 | Fixing of AC/DC Panel and giving Connections to the protection equipment and Metering circuits as per the specification and standards. The 3 1/2 core 25 Sqmm power cable required from distribution box to AC/DC panel in the control room is also to be supply | Supply work | Supply of work | As per relevent standard specification | 7871.85 | SET | 15743.7
70 | SWR20768 | 26 | Earth work excavation of in all soils except hard rock requiring blasting. | Earthing work | Earthing of work | As per relevent standard specification | 345 | M3 | 8970
Schedule Cost. (Excluding GST) | [8 empty] | 1295146.598
33 KV/11 KV line
1 | SWR22092 | 0.18 | survey line&cabl inc peg mark&tree clear | Laying work | Laying of work | As per relevent standard specification | 765 | KM | 137.7
2 | SWR11230 | 2 | Loading of 11/33KV XLPE UG Cable for all sizes | LOADING work | LOADING of work | As per relevent standard specification | 1024 | DR | 2048
3 | SWR11860 | 2 | Transport of conductor drums, cable drums, fragile material such as kiosks, VCBs, control panels, current transformers, boosters, lightning arrestors, insulators, transformers, meters (which are less in weight and occupy more space) (excluding of loading unloading) Note: 1). It will be treated as full load of 10 MT and paid for 10 MT. 2). For 3 Ton vehicle : 50% of the following rates Upto 10 Km with Lorry for each trip | Transport work | Transport of work | As per relevent standard specification | 2720.34 | EA | 5440.68
4 | SWR11231 | 2 | Unloading of 11/33KV XLPE UG Cable all sizes | UNLOADING work | UNLOADING of work | As per relevent standard specification | 1024 | DR | 2048
5 | SWR11972 | 180 | Laying of XLPE UG cable Double Run including excavation of trench of size 600mm wide and 850mm for LT, 1050mm for 11 KV and 1200mm for 33 KV from road level and cable separation with machine cut bricks horizontally for every 3 meters , providing of DWC/GI pipes wherever required depth is not acquired as per the instructions of Engineer in Charge, the prorata basis rates to be adopted for 2 feet, 3feet depths and filling with sand 250mm above the cable and 50mm below the cable, laying of cable, placing 40mm shabad protective slabs, back filling the trench with earth, levelling and removing the debris from the site inluding the cost of lead and lift etc.. (Second cable laying cost not Included) depth of the trench LT-0.85 mts, 11 KV-1.05Mtrs & 33 KV - 1.20 mtrs.33 KV 3x400 Sqmm Cable | Laying work | Laying of work | As per relevent standard specification | 749 | M | 134820
6 | SWR10988 | 180 | Laying of 2nd cable in excavated trench | Laying work | Laying of work | As per relevent standard specification | 204.1 | M | 36738
7 | SMR40081 | 20 | Cost of Pipes and slabs Supply of 6" B Class GI pipe 5mm thck 20Kg/M | Laying work | Laying of work | As per relevent standard specification | 1044 | M | 20880
8 | SWR10387 | 4 | Making of Outdoor/Indoor End Termination 33 KV 3x400 Sqmm Cable | Laying work | Laying of work | As per relevent standard specification | 2764.76 | EA | 11059.04
9 | SWR12004 | 40 | Raising of double run cable on already erected support with wooden / MS clamps and connecting it to over head line with cable jumpers including cost of required wooden cleats, lugs and bolts and nuts through GI pipe (excluding the cost of GI pipe)33 KV 3x400 Sqmm Cable | Raising work | Raising of work | As per relevent standard specification | 323.85 | M | 12954
10 | SWR10206 | 0.17 | LOADING of MS Channel,Angles,Flats&Rods | LOADING work | LOADING of work | As per relevent standard specification | 221 | TO | 37.57
11 | SWR10524 | 0.17 | UNLOADING of MS Channel,Angles,Flats&Rod | UNLOADING work | UNLOADING of work | As per relevent standard specification | 185 | TO | 31.45
12 | SWR10204 | 4 | LOADING of R.S. Joists 175 x 85 mm | LOADING work | LOADING of work | As per relevent standard specification | 76 | EA | 304
13 | SWR10132 | 1.17 | Transport of iron materials such as R.S. Joists, Rail Poles, fabricated supports, steel, iron, flat, M.S. Channels etc., by lorries. (excluding of loading & unloading )Above 10 KM and upto 20 KM | Transport work | Transport of work | As per relevent standard specification | 412.08 | TO | 482.1336
14 | SWR10522 | 4 | UNLOADING of R.S. Joists 175 x 85 mm | UNLOADING work | UNLOADING of work | As per relevent standard specification | 50 | EA | 200
15 | SWR10642 | 4 | Fabrication of 175x85/150x75mm RS joist pieces upto 12.5 meters length by welding joint together by means of 50x6mm flat and MS channel on either side including the cost of consumable. | Fabrication work | Fabrication of work | As per relevent standard specification | 512.55 | EA | 2050.2
16 | SWR10640 | 2 | Painting of R.S Joist,Box poles including cross arms and clamps with one coat of red oxid and two coats of Al.paint including cost of paint and consumables | Erection work | Erection of work | As per relevent standard specification | 1132 | EA | 2264
17 | SWR11040 | 2 | Excavation of pits in hard rock not requiring blasting. (In hard murram / rock boulders)0.75 M x 0.9 M x 1.95 M | Excavation work | Excavationof work | As per relevent standard specification | 990.68 | EA | 1981.36
18 | SWR11266 | 2 | Erection of pole in position, aligning and setting to work, fixing of cross arms and top clamps, earthing of supports,back filling with earth and stones properly ramming including transport of materials from road side to location excluding pit excavation Box pole 9/10/11 Mtr | Erection work | Erection of work | As per relevent standard specification | 2643.83 | EA | 5287.66
19 | SWR10356 | 1.88 | Mass concreting of supports erected with CC (1:4:8) using 40 mm, HB G metal including the cost of metal, sand,Cement and curing etc.Including the cost of cement | Erection work | Erection of work | As per relevent standard specification | 6579 | M3 | 12368.52
20 | SWR11890 | 0.06 | Mass Concreting for pole Coping of 1.5'x1.5'x1 with 1:8 slope Using form boxes (0.031Cumt.) | Erection work | Erection of work | As per relevent standard specification | 3893 | M3 | 233.58
21 | SWR10869 | 0.17 | Fabrication of Main and Auxiliary structures with welding using raw steel such as RS joist, M.S.Angles, Plates, Channels, including the supply and fabrication of 6mm base plate to the RS-Joist poles excluding cost of Mild Steel and transport charges to substation site, including erection. | Fabrication work | Fabrication of work | As per relevent standard specification | 3426 | TO | 582.42
22 | SMR11483 | 2 | Supply of CI eath pipe with 80mm dia,2.0 M Length | Supply work | Supply of work | As per relevent standard specification | 2789 | EA | 5578
23 | SWR10357 | 2 | Providing of earthing with excavation of earth pit (0.6 x0.6x2.4 Mts.) duly filling with bentonite, earth , running of earth wire etc., complete, including cost of bentonite and excluding cost of RCC collar of size 0.6M dia x 0.5 M height . | Earthing work | Earthing of work | As per relevent standard specification | 1234.2 | EA | 2468.4
24 | SWR10359 | 2 | Providing of RCC Collar guarding to the existing earth pits with damaged masonry including dismantling and removing of existing masonry and fixing the RCC collar of 0.60 M dia X 0.50 M height | Earthing work | Earthing of work | As per relevent standard specification | 386 | EA | 772
25 | SMR40085 | 10 | Supply of RCC cable Joint markers/ Cable route markers of size 700 X 240 X 75 mm duly engraving with 5 mm thick letters , CPDCL 33000/11000 Cable/Cable joint fixing the 300mm below ground level and 400mm above ground level confirming to IS 5820 2001 | Supply work | Supply of work | As per relevent standard specification | 484 | EA | 4840
26 | SWR12101 | 4 | Painting of feeder name on support including cost of paint | Erection work | Erection of work | As per relevent standard specification | 53 | EA | 212
27 | SMR11488 | 12 | Supply of earthing pipe with materials Supply of GI Bolts & Nuts etc | Earthing work | Earthing of work | As per relevent standard specification | 117.5 | KG | 1410
28 | SWR10346 | 3 | Erection of pole in position, aligning and setting to work, fixing of cross arms and top clamps, earthing of supports,back filling with earth and stones properly ramming including transport of materials from road side to location excluding pit excavation RS Joists 150x75/175 x 85 mm | Erection work | Erection of work | As per relevent standard specification | 1934 | EA | 5802
29 | SWR11873 | 6 | Cutting charges for MS Sections MS Channel 75 x 40 mm | Erection work | Erection of work | As per relevent standard specification | 9 | EA | 54
30 | SMR11487 | 20 | Supply of earthing pipe with materials Supply of MS bolts & nuts and washers etc of all sizes | Supply work | Supply of work | As per relevent standard specification | 91.25 | KG | 1825
31 | SMR40132 | 12 | Supply of 120 Sqmm Aluminium lugs | Supply work | Supply of work | As per relevent standard specification | 12.52 | EA | 150.24
32 | SWR11039 | 3 | Excavation of pits in hard rock not requiring blasting. (In hard murram / rock boulders)0.76 M x 0.76M x 1.83M (2.6" x 2.6" x 6.0") | Excavation work | Excavation of work | As per relevent standard specification | 928 | EA | 2784
33 | SWR10320 | 8 | Fabrication of materials including 2 coats of Red oxide painting Back clamps with 50 x 6 mm MS Flat | Fabrication work | Fabrication of work | As per relevent standard specification | 15 | EA | 120
34 | SWR10454 | 0.45 | Stringing of HT AB Cable with GI Metal Parts HT AB Cable 11 KV 3x185+70 Sqmm | Stringing work | Stringing of work | As per relevent standard specification | 41876.11 | KM | 18844.2495
35 | SMR11504 | 6 | End Termination of AB cable (each lead):Supply of 11KV 3x185+70sq.mm/3x70+70sq.mm/3x35+35sq.mm AB cable end Kits | End Termination work | End Termination of work | As per relevent standard specification | 950 | SET | 5700
36 | SWR10667 | 6 | End Termination of AB cable (each lead):120 Sqmm to 185 Sqmm | End Termination work | End Termination of work | As per relevent standard specification | 800 | EA | 4800
37 | SWR10673 | 10 | Straight through joints of AB cable (each lead)Supply and ere Angle line Asmbly kits | Supply work | Supply of work | As per relevent standard specification | 2124 | EA | 21240
38 | SWR10672 | 10 | Straight through joints of AB cable (each lead)Supply and ere Straight line Asmbly kits | Supply work | Supply of work | As per relevent standard specification | 1661 | EA | 16610
39 | SMR12099 | 20 | Supply and Erection of I Hook and Suspension Hook Supply of I Hook | Supply work | Supply of work | As per relevent standard specification | 158 | EA | 3160
40 | SWR12099 | 20 | Supply and Erection of I Hook and Suspension Hook Erection of I Hook | Supply work | Supply of work | As per relevent standard specification | 55 | EA | 1100
41 | SWR11863 | 1 | Transport of conductor drums, cable drums, fragile material such as kiosks, VCBs, control panels, current transformers, boosters, lightning arrestors, insulators, transformers, meters (which are less in weight and occupy more space) (excluding of loading unloading) Note: 1). It will be treated as full load of 10 MT and paid for 10 MT. 2). For 3 Ton vehicle : 50% of the following rates Above 30 Km and upto 50 Km with Lorry for each trip | Transport work | Transport of work | As per relevent standard specification | 4372.74 | EA | 4372.74
42 | SWR10131 | 1.6 | Transport of iron materials such as R.S. Joists, Rail Poles, fabricated supports, steel, iron, flat, M.S. Channels etc., by lorries. (excluding of loading & unloading )Upto 10 KM | Transport work | Transport of work | As per relevent standard specification | 339.66 | TO | 543.456
43 | SWR24971 | 3 | Supply and erection of T-Branch kit | Supply work | Supply of work | As per relevent standard specification | 3215 | EA | 9645
44 | SWR10671 | 3 | Erection of Assemble Kit for 'T' Branche | Erection work | Erection of work | As per relevent standard specification | 1800 | EA | 5400
45 | SWR10204 | 6 | LOADING of R.S. Joists 175 x 85 mm | LOADING work | LOADING of work | As per relevent standard specification | 76 | EA | 456
46 | SWR10522 | 6 | UNLOADING of R.S. Joists 175 x 85 mm | UNLOADING work | UNLOADING of work | As per relevent standard specification | 50 | EA | 300
47 | SWR22065 | 0.36 | LT Lines - Dismantling of 11KV 34/55 sqmm SC | Dismantling work | Dismantling of work | As per relevent standard specification | 4500 | KM | 1620
48 | SWR11321 | 1 | Dismantling of Damaged Poles, not required and available in the middle of roads, transporting to stock point etc. 11 Mtrs PSCC poles | Dismantling work | Dismantling of work | As per relevent standard specification | 1896.18 | EA | 1896.18
49 | SWR11320 | 2 | Dismantling of Damaged Poles, not required and available in the middle of roads, transporting to stock point etc.Dism of 9.1M PSCC Pole | Dismantling work | Dismantling of work | As per relevent standard specification | 948.09 | EA | 1896.18
50 | SWR11319 | 3 | Dismantling of Damaged Poles, not required and available in the middle of roads, transporting to stock point etc.- 8.0 m long PSCC pole | Dismantling work | Dismantling of work | As per relevent standard specification | 501.53 | EA | 1504.59
51 | SMR40009 | 1.5 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Supply of material cost for First coat of 1st Grade Aluminium Paint,brushes etc. | Erection work | Erection of work | As per relevent standard specification | 2181 | TO | 3271.5
52 | SWR10877 | 1.5 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Labour charges for painting including scratching and cleaning of Substation structures of 1st coat of Aluminium | Erection work | Erection of work | As per relevent standard specification | 851 | TO | 1276.5
53 | SMR40010 | 1.5 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Supply of material cost for Second coat of 1st Grade Aluminium Paint,brushes, etc. | Erection work | Erection of work | As per relevent standard specification | 1293 | TO | 1939.5
54 | SWR10879 | 1.5 | Painting of sub-station structures with two coats of Aluminium paint using Aluminium paint 1st grade containing 3.6 kg of Aluminium paste for 18 liters of thinner 1st coat is to be applied Supply of material cost for Second coat of 1st Grade Aluminium Paint,brushes, etc. | Erection work | Erection of work | As per relevent standard specification | 482 | TO | 723
55 | SWR10867 | 1.5 | Alligning the Main/Aux. structures. | Erection work | Erection of work | As per relevent standard specification | 1470 | TO | 2205
56 | SWR11267 | 6 | Erection of pole in position, aligning and setting to work, fixing of cross arms and top clamps, earthing of supports,back filling with earth and stones properly ramming including transport of materials from road side to location excluding pit excavation Box pole 12 Mtr | Erection work | Erection of work | As per relevent standard specification | 3901.37 | EA | 23408.22
57 | SWR10356 | 1.24 | Mass concreting of supports erected with CC (1:4:8) using 40 mm, HB G metal including the cost of metal, sand,Cement and curing etc.Including the cost of cement | Mass concreting work | Mass concreting of work | As per relevent standard specification | 6579 | M3 | 8157.96
58 | SWR10862 | 2.31 | Plastering 2 Coats,20/16mm(1:6)(1:4) | Erection work | Erection of work | As per relevent standard specification | 373 | M2 | 861.63
59 | SWR11089 | 4 | Paint of coping with 2 coats of white cement incl cost of paints etc. | Erection work | Erection of work | As per relevent standard specification | 48 | EA | 192
Schedule Cost. (Excluding GST) | [8 empty] | 419087.6591
|  |  | Schedule Cost. (Excluding GST) | 3778315.3321
|  |  | GST@18% | 680096.7598
|  |  | Schedule Cost. (Excluding GST) | 4458412.0919